## Product Backlog
Product Backlog
StoryID | Story name | Status | Size | Sprint | Comments
1 | The program can be accessed from different computers | Done | 6 | 3 | Create RMI connection between main computer and two host computers
2 | Factory pattern for rooms | Done | 3.5 | 1 | With this pattern we make different types of rooms
3 | Server implements singleton pattern | Done | 1 | 3 | Through this pattern we create server uniqe object
4 | MVC | Done | 12 | 5 | Console menu is created with MVC design pattern
5 | Iterator pattern | Done | 1.5 | 6 | For going through lists of different objects.
6 | Look for available rooms by given dates | Done | 3 | 4 | Display list of available rooms in given period of time
7 | Look for booked rooms by given dates | Done | 3 | 4 | Display list of booked rooms in given period of time
8 | Guest and Booking classes | Done | 2.5 | 1 | Making these classes for easier implementation later
9 | Console interface for testing purposes | Done | 2 | 6 | Create console menu for testing different tasks
10 | Book a room | Done | 9 | 2 | The core of the system. The idea is that the receptionst can store the guest information.
11 | Edit information about bookings/check-ins | Done | 2 | 6 | All information about guests can be edited by the receptionist.
12 | Store data in external files | Done | 2 | 6 | Store and load data from an external file
|  | Total : | 47.5
Planned
Done
OnGoing
Deleted

## Release Burndown
Release Burndown Chart
Sprint | Total | Planned Work | Realized Work | Remaining Work
1 | 47.5 | 6 | 6 | 41.5
2 | 41.5 | 9 | 9 | 32.5
3 | 32.5 | 7 | 7 | 25.5
4 | 25.5 | 6 | 6 | 19.5
5 | 19.5 | 12 | 12 | 7.5
6 | 7.5 | 7.5 | 7.5 | 0
0
Ideal
7.9167
47.5
39.5833
31.6667
23.75
15.8333
7.9167
0

## Sprint1
Sprint 1
StoryID | ITEM DESCRIPTION | Responsible | Hours | Day 1 | Day 2
6
8 | Guest and booking classes
8 | Implement class guest | Stefan | 1 | 0 | 0
8 | Implement class booking | Daniel | 1 | 0 | 0
8 | Test | Stefan | 0.5 | 0 | 0
2 | Factory pattern for rooms
2 | Create abstract class room | Atanas | 1.5 | 1 | 0
2 | Implement 4 sub classes | Stefan | 0.5 | 0.5 | 0
2 | Create class roomFactory | Atanas | 1 | 1 | 0
2 | Make Junit test | Daniel | 0.5 | 0.5 | 0

## Sprint2
Sprint 2
StoryID | ITEM DESCRIPTION | Responsible | Hours | Day 1 | Day 2
9
10 | Book a room
10 | Create list of default rooms | Atanas | 1 | 0 | 0
10 | Create addBooking method | Daniel | 1 | 0 | 0
10 | Make it impossible to book a room for already booked date | Atanas | 3 | 0 | 0
10 | Sort bookings by startDate | Atanas | 2 | 2 | 0
10 | Test booking | Stefan | 2 | 2 | 0

## Sprint3
Sprint 3
StoryID | ITEM DESCRIPTION | Responsible | Hours | Day 1 | Day 2
7
1 | The program can be accesed from different computers
1 | Create server class | Atanas | 2 | 0 | 0
1 | Create client class | Daniel | 1 | 0 | 0
1 | Implement sharedInterface | Stefan | 0.5 | 0 | 0
1 | Test connection | Daniel | 2.5 | 2 | 0
3 | Server using singleton pattern
3 | Implement singleton design pattern for server class | Stefan | 1 | 1 | 0

## Sprint4
Sprint 4
StoryID | ITEM DESCRIPTION | Responsible | Hours | Day 1 | Day 2
6
6 | Look for available rooms by given dates
6 | Implement method which checks if a room is free in given time period | Atanas | 2 | 0 | 0
6 | Create method which creates list of available rooms | Stefan | 0.5 | 0 | 0
6 | Test | Daniel | 0.5 | 0.5 | 0
7 | Look for booked rooms by given dates
7 | Implement method which checks if a room is occupied in given time period | Atanas | 2 | 1 | 0
7 | Create method which creates a list of booked rooms | Daniel | 0.5 | 0.5 | 0
7 | Test | Daniel | 0.5 | 0.5 | 0

## Sprint5
Sprint 5
StoryID | ITEM DESCRIPTION | Responsible | Hours | Day 1 | Day 2
12
4 | MVC
4 | Implement classes model, view and controller for client | Stefan | 1 | 0 | 0
4 | Implement classes model, view and controller for server | Daniel | 2 | 0 | 0
4 | Connect model and view class via controller for client | Daniel | 3 | 0 | 0
4 | Connect model and view class via controller for server | Atanas | 5 | 5 | 0
4 | Test | Atanas | 1 | 1 | 0

## Sprint6
Sprint 6
StoryID | ITEM DESCRIPTION | Responsible | Hours | Day 1 | Day 2
7.5
9 | Console interface for testing purposes
9 | Create console menu | Atanas | 1.5 | 1 | 0
9 | Test | Daniel | 0.5 | 0.5 | 0
5 | Iterator pattern
5 | Create iterator class | Stefan | 0.5 | 0 | 0
5 | Implement iterator on client side | Stefan | 0.5 | 0 | 0
5 | Test | Stefan | 0.5 | 0 | 0
11 | Edit information about bookings/check-ins
11 | Create new method to edit existing bookings | Atanas | 1.5 | 0 | 0
11 | Test | Daniel | 0.5 | 0.5 | 0
12 | Store data in external files
12 | Create save method | Atanas | 1 | 1.5 | 0
12 | Create load method | Daniel | 0.5 | 0.5 | 0
12 | Test | Daniel | 0.5 | 0.5 | 0